## Public
Council Effectiveness | Activity | Rationale | Process | Time scale | Who | Next steps? | Current Progress | Next Parish Council Meeing update due | Notes
Protect and enhance natural and built environments within the Parish | Plant trees to make the environment greener. | Areas such as Faulkener’s Way and the High Road (and other areas) would be greatly enhanced by sensitive planting. | Seek advice and funding from Woodland Trust and Local Authorities. Identify areas for tree planting taking account of planned developments. | As soon as possible | Lynn | Location for planting is required, contact to be made with Taryn Mason (Trees for Felixstowe) also Suffolk Wildlife Trust. St Mary's Green to be pursued as an option. | On hold until Autumn. Location for planting required, contact made from Taryn Mason. Trees for Felixstowe. Suffolk Wildlife trust. Also, pursue St Mary's Green as an option for planting. | 2021-09-01 | Meet with Taryn (Lynn to arrange)
| Tidy / renovate mini-roundabout verges | Area has become untidy and if well-kept it is likely to deter nuisance parking | Prososal to be returned to PC | 2020-11-01 | Lynn | Lynn to deliver some bulbs to Lynn and Angela for planting when suitable. | Lynn has met with Angela and Nina who have very kindly been looking after the flower beds around the mini areas for many many years, they have agreed to continue. Councillors agreed for Debbie to instruct the gardeners on a one off visit to the area to cut back grass over cycle path to the original edge and road and a one off cut and weed. |  | March agenda for annual planting
| Enhance ‘Old Trimley’ in the vicinity of the church and Welcome Hall. | The centre of ‘Old Trimley’ around the village church, pub and Parish Hall is untidy and congested, and yet offers great opportunity as a village centre. | Consult community, seek advice, draw up plans. | By Summer 2023 | Lynn Beal | Install temporary flagpole | Bulb planting done, railings painted, bench and fence repaired. New notice board installed | June 21 (to discuss installation)
| Maintain and upkeep bus shelters (cleaning etc.) | Without regular cleaning the bus shelters become untidy and unwelcoming to use | Agree cleaning contract with local supplier | Summer 2021 | Clerk | Discussions with Norse, Shirley Shelley etc. | Quotes for cleaning are being obtained New bins has been ordered for the bus shelter near Stennetts field | 2021-06-01
Reduce the impact of noise pollution from both the A14 and the Railway | Develop a noise mitigation strategy | Increasing levels of traffic have greatly increased noise pollution | Liaise with Highways England the port authority and Suffolk CC |  | Andrew | Explore how planting of trees and shrubs can be used for noise reduction. Pursue Highways to honour agreement to plant trees/shrubs on Thurman’s lane embarkment - still active. Continue to engage Matthew homes on enhancing noise mitigation measures as part of the Thomas Ave development - Debbie to follow up Port traffic is major contributor to local noise pollution, contribution from port authority could be sought to help mitigate this impact. | Engagement with ESC, Highways etc to: 1) reduce the impact of proposed resurfacing works 2) ensure that proposed works deliver the maximum possible reduction in traffic noise, once complete 3) Deliver tree planting on Thurmans lane embankment | 2021-09-01
Reduce Pollution | Assess and monitor air pollution | Increased traffic has had an unknown effect on air quality | Work with the Air Quality Commission, Highways and the Port Authority to improve air quality |  | Bryan - Rail | Brian to engage Network Rail to: 1) discuss the installation of signs to notify drivers to swith off engines whilst waiting at the railway crossing 2) Discuss alternative solutions that could reduce the wait times at the barrier crossing | Continue to engage Network rail Continued engagement with the Local Authority Liaison Committee (LALC) to understand proposed environmental / air quality enhancements |  | Look to address length barriers are down (agenda for next LALC)
Improve Road Safety | Provide further Pedestrian Crossing in the vicinity of the church/pub. | Additional housing has increased the number of pedestrians. The road here is very busy and a crossing will improve residents safety. | Liaise with planning and highways departments. Seek this as a condition for planning on Howlett Way. Seek to work in partnership with Trimley St Martin. Seek CIL funding. | By July 2023 | Clerk, Chair | Review Howlett way development plans - when available - to understand the proposed type of crossing and ensure fitness for purpose. Reeve lodge are also proposing a crossing nearby, this needs review to ensure viability. | Agreement has been reached that crossing will be delivered as part of the Howlett Way development (at no cost to TPC)
| Reduce traffic speeds | Parts of the village suffer from excess traffic speeds | Buy another Speed Indicator Device |  | Colin | Review effectiveness, informed by the data the new SID collects | SID has been installed | 2021-09-01
|  |  | Add further mini roundabouts |  | Gareth | Investigate if any of the S106 from the Thomas Ave development or CIL money could be directed to fund new mini roundabouts to reduce the impact of additional traffic caused by this (and other) local developments. | Roadside origin study completed for inclusion in planning application responses | 2021-10-01
| Improve existing footpaths/bridle ways | Many footpaths are overgrown with uneven and unstable footing | Work with SCC Highways - Footpaths and Bridle ways |  | Colin | Mathew homes as part of the Thomas Avenue development will resurface footpath 11. | Maintenance to footpath 11 is underway to repair overgrown trees / shrubs. Maintenance of overgrowth on the footpath to the side of A14 is being addressed. | The condition of the public footpath near the new rifle range has been pursued with SCC and Bidwells been repaired
| Renew and improve road markings | Many are worn out, and there are few double yellow lines to restrict parking in key bottlenecks | Liaise with SCC Highways, introduce No Parking By Laws, press ESC to enforce parking restrictions |  | Bryan | (NOTE: Cycle lanes to be re-painted. This also has the benefit of narrowing the highway, focussing driver attention and reducing speeds.) Indicative cost to be sought. Possible join up with Felixstowe to be considered. | Some white lines have been re-painted in key areas |  | Cross boundary group
| Designate footpath parking zones | Often cars are parked too close to walls/hedges/fencing for wheelchairs/prams/pedestrians to pass safely. | Introduce dotted white lines on pavements to indicate acceptable parking zones |  | Bryan | Suggestions to be made to Linda (none received) David to speak to Rachel Partridge (parking enforcement officer) about regular trouble spots (near chip shop, narrow pavement between Station road / New road, faulkeners way commercail vehicle parking) Debbie to speak to Stuart Bird Lynn to Speak to Graham Newman |  | 2021-10-01
| Seek to provide car parking in key places including the vicinities of the church and the school. | Car parking is an issue around the school and in the vicinity of church, shop and pub. Parking would be easier and traffic would flow better if parking was provided. | Identify potential areas for a car park. Identify how land can be acquired. Buy the land and build the car park(s) | Liaise with ESC by summer 2023 | Traffic working | David & Andrew to ask Trinity College for a 99 year lease (or buy) the field behind Welcome hall. Potential for compulsory purchase to be explored, if no agreement made. Double yellow on Trimley St Mary side of the High road as far as Gun Lane. Lynn / Linda to survey the residents for any objections. | Ongoing discussions with Bidwells / ESC / Trimley St Martin PC
| Safe haven / footpath down Thurmans lane | Recent development has significantly increased the level of pedestrations that use Thurmans lane. The road is a narrow single lane than only has sufficient width for one car. There is no dedicated pedestrian walkway and pedestrians are placed at risk when using the lane. Any additional development will increase the number of pedestrians that use this road. | Look to ensure that additional development provides funding to support additonal demand / risk to pedestrians on Thurmans lane. |  | Andrew | S106 request in Howlett way development | Request S106 funding to support dedicated pedestrian access down Thurmans lane. | 2021-06-01
Improve, increase and protect recreational and green space | Maintain green space aroudn village to prevent coalesence | Prevent inappropriate development of village assets | Engage local authority and land owners to promote appropriate use of the land | Summer 2021 | David / Gareth | Land formerly protected from development and land behind Welcome hall to be applied for. Discussion to be had about land formerly protected from development in Eastern Trimley potentially being availble for open space recreation | Continuing to engage with land owners
| Acquire new land for recreational use | The area of recreational space per capita is below national standards | Contact District Council and local landowners to identify such areas and make proposals for taking over ownership. | Summer 2021 | David | Options may include: Land between railway and Great Street farm. Extending stennetts as a playing field and/or providing a parking facility. Extending the allotments to Gun Lane. Coatsmith field. | Discussion with Bidwells regarding the potential to gift land to the Parish for recreational use.
| Update the play equipment on St Mary's Green | The play equipment is now very old and should be brought up to modern standards | Discuss with ESC who own and mange the facility |  | Gareth / Colin | Revisit discussion with ESC | Engaging with ESC to understand current plans for refreshing equipment. Spoke to Sarah Shinnie. Limited funds available (£15k across south of region), we have limited S106 money availble to us (£111) Sarah to update once Norse have carried out inspection, there may be something they can suggest. Other options are Big Lottery (not ideal at the moment as they are focussing on Covid projects) or approaching PoF? |  | Check with ESC?
| Support and protect both our Area of Outstanding Natural Beauty and the Nature Reserve | In addition to protecting wildlife and their environment, these are nationally important recreational space | Seek to engage more frequently with the management of these valuable environmental assets |  | David / Gareth | Establish engagement and invite to Parish Council meeting? | Potential to fund new signage with Suffolk Wildlife within Trimley St Mary. Could look to bring together with the walking maps being developed by residents Andrew to engage SWT contact to become more active with the PC
Enhance and develop existing Recreational and Leisure Facilities | Develop additional sporting facilities at Stennets Field. | We have a good resource which is well used for football but has scope for other uses | Identify sporting requirements in conjunction with East Suffolk and their plans for a new leisure facility |  | David | Explore the feasibility of an all-weather pitch, potential to explore the land next to Stennetts field
| Support the arts through the Arts Centre or through supporting other arts initiatives. | The Arts make use of village amenities that would otherwise fall into disrepair | Consider individual requests for funding as and when they arise |  | Clerk | All requests are considered upon submission PC to consider funding display boards | Provide funding to 2Sisters and the welcome hall supports also support performing arts activities Presentation boards purchased to support Artists
Support and develop our charitable trusts | Improve the Welcome Hall | The facility is in need to updating and could become a far more popular and effective asset for the village | Consult with management committee |  | Colin, Lynn | Discussion around booking at St Martin to be had - is there opportunity to generate additional Damp near disused entrance to be addressed | Interior furnishing has been updated. This improving the hall's acoustics as well as appearance. Interior re-painting completed. Outside Bench repaired and refurbished. | June 21 (to discuss installation) | Consider engaging a handyman (Susan)
| Improve and support the Town Field Allotment Gardens | Allotment | Consult with management committee |  | Lynn | Investigate options for improving water extraction from the bore hole Clarify obligatin to provide minimum number of allotments and who this obligation falls to | Access road repairs/ improvement completed. New bench installed. Some plots halved to increase capacity
Support the social needs of all age groups within the Parish | Support the Trimley Station Trust | Trimley Station is a unique historical resource which can be saved for the village. | Liaise with the Trimley Station Trust. | Offer support in 2019 for stage 1 of the development. | Bryan | Update on progress from the Trimley Station Trust?
| Support Rosebury Cottage | The Café provides meals for the under privileged and vulnerable | Seek to provide funding to allow for further activities at the Cafe |  | David |  | On hold due to Covid restrictions
| Encourage third party support organisations to set up within the village | While facilities such as Citizens Advice and Age Concern can be found in Felixstowe, there is no local facility within the village. | Make accommodation available for drop-in centres |  | Colin | Discuss the use of Welcome Hall for drop-ins from these services? | On Hold due to COVID-19
Develop and improve the knowledge of Councillors | Provide funding for Councillor Training | We wish our councillors to be as highly trained as possible so they can make full use of local knowledge. | Offer high quality training to councillors through Suffolk Association of Local Councils and other sources, circulate training information. | Ongoing | All councillors and clerk. |  | 2 new Councillors have completed the SALC provided new Councillor training
Improve communication with residents and other stake holders | Make best use of the website and Face Book page | Many residents use the internet and Social Media to keep up to date with local developments | Increase in volume, and more timely publication of information | Ongoing | Colin / Andrew / Lynn |  | October 2020 update: Likes have gone by over 80, up 206% Page views have gone up 791% Post engagements have gone up 5000 up 6855%
| Use the Parish Magazine as a means on informing and engaging with residents. | Not all residents are active on line, we need an additional means of communicating developments | Aim to produce and distribute the magazine to all residents 3 times a year. | 2020-03-01 | Lynn with others |  | Monthly summary to be published on FB and in the local free press (Felixstowe Spotlight).
| Seek feedback from residents | Ensure the activities of the Parish Council reflect the needs of residents | Develop consultation events to engage residents though, for example, parish meetings, drop in sessions or the APM | Annually | Chair, Clerk. | Consider promoting through the newsletter, FB, drop ins etc
| Support local events | Parish funds should be spent on Parish activities | Identify ways in which we can support activities within the parish, such as Christmas celebrations, Carnival, Football tournament etc | Ongoing | Chair Clerk | Continue to seek opportunities | PC supporting Rosebury café for community events and Trimley Red Devils
| Recruit additional Parish Councillors | Ensure vibrant Parish Council with active members | Consider opportunities to engage potential Parish Councillors | Ongoing | All councillors and clerk. | When Pandemic conditinos allow, invite Parish Praise receivers, local businesses etc to AGM or similar to raise awareness of Parish Council |  | 2021-11-01
| Encourage Village cohesion | Trimley St Mary is a ribbon village with clusters of housing that do not always work together | Identify activities that bring the entire village together, make use of the Community Partnership Funding. |  | Lynn | Make the Annual parish meeting a larger event i.e. invite parish praise recipients. | Parish praise certificates awarded to businesses and individuals who supported Trimley throughout lockdown
Ensure the Parish Plan remains relevant | Monitor the changing demographics of the Parish | Changing populations have different needs | Obtain detailed demographic information and identify areas of future need | Annually | All councillors and clerk. | Review after next census is published |  | 2021-12-01

## Costed
Council Effectiveness | Activity | Rationale | Process | Time scale | Who | Cost
Protect and enhance natural environments within the Parish | Plant trees to make the environment greener. | Areas such as Faulkener’s Way and the High Road (and other areas) would be greatly enhanced by sensitive planting. | Seek advice and funding from Woodland Trust and Local Authorities. Identify areas for tree planting taking account of planned developments. | As soon as possible | Lynn & Linda | Max £1000
| Tidy / renovate mini-roundabout verges | Area has become untidy and if well-kept it is likely to deter nuisance parking | Prososal to be returned to PC | 2020-11-01 | Lynn & Linda
| Enhance ‘Old Trimley’ in the vicinity of the church and Welcome Hall. | The centre of ‘Old Trimley’ around the village church, pub and Parish Hall is untidy and congested, and yet offers great opportunity as a village centre. | Consult community, seek advice, draw up plans. | By Summer 2023 | Lynn Beal | Expenses
Reduce the impact of noise pollution from both the A14 and the Railway | Develop a noise mitigation strategy | Increasing levels of traffic have greatly increased noise pollution | Liaise with Highways England the port authority and Suffolk CC |  | Andrew
| Develop a noise mitigation strategy | Addition of the passing loop and increase in rail traffic has increased noise pollution | Liaise with Network Rail and the Port Authority
Reduce Pollution | Assess and monitor air pollution | Increased traffic has had an unknown effect on air quality | Work with the Air Quality Commission, Highways and the Port Authority to improve air quality |  | Bryan - Rail
Improve Road Safety | Provide further Pedestrian Crossing in the vicinity of the church/pub. | Additional housing has increased the number of pedestrians. The road here is very busy and a crossing will improve residents safety. | Liaise with planning and highways departments. Seek this as a condition for planning on Howlett Way. Seek to work in partnership with Trimley St Martin. Seek CIL funding. | By July 2023 | Clerk, Chair | 20000
| Reduce traffic speeds | Parts of the village suffer from excess traffic speeds | Buy another Speed Indicator Device |  | Colin
|  |  | Add further mini roundabouts |  | Gareth
| Improve existing footpaths/bridle ways | Many footpaths are overgrown with uneven and unstable footing | Work with SCC Highways - Footpaths and Bridle ways |  | Colin
| Renew and improve road markings | Many are worn out, and there are few double yellow lines to restrict parking in key bottlenecks | Liaise with SCC Highways, introduce No Parking By Laws, press ESC to enforce parking restrictions |  | Bryan
| Designate footpath parking zones | Often cars are parked too close to walls/hedges/fencing for wheelchairs/prams/pedestrians to pass safely. | Introduce dotted white lines on pavements to indicate acceptable parking zones |  | Linda
| Seek to provide car parking in key places including the vicinities of the church and the school. | Car parking is an issue around the school and in the vicinity of church, shop and pub. Parking would be easier and traffic would flow better if parking was provided. | Identify potential areas for a car park. Identify how land can be acquired. Buy the land and build the car park(s) | Liaise with ESC by summer 2023 | Traffic working | 15000 | Bidwells to be approached about to the availability of the entrance to Great Street farm for parking?
| Safe haven / footpath down Thurmans lane | Recent development has significantly increased the level of pedestrations that use Thurmans lane. The road is a narrow single lane than only has sufficient width for one car. There is no dedicated pedestrian walkway and pedestrians are placed at risk when using the lane. Any additional development will increase the number of pedestrians that use this road. | Look to ensure that additional development provides funding to support additonal demand / risk to pedestrians on Thurmans lane.
Improve, increase and protect recreational and green space | Protect assets of community value from development | Prevent inappropriate development of village assets | Identify and register Assets of Community Value |  | Bryan
| Acquire new land for recreational use | The area of recreational space per capita is below national standards | Contact District Council and local landowners to identify such areas and make proposals for taking over ownership. |  | David
| Update the play equipment on St Mary's Green | The play equipment is now very old and should be brought up to modern standards |  | Colin | Gareth
| Support and protect both our Area of Outstanding Natural Beauty and the Nature Reserve | In addition to protecting wildlife and their environment, these are nationally important recreational space | Seek to engage more frequently with the management of these valuable environmental assets |  | David
Enhance and develop existing Recreational and Leisure Facilities | Develop additional sporting facilities at Stennets Field. | We have a good resource which is well used for football but has scope for other uses | Identify sporting requirements in conjunction with East Suffolk and their plans for a new leisure facility |  | Chair, Clerk | 15000
| Support the arts through the Arts Centre or through supporting other arts initiatives. | The Arts make use of village amenities that would otherwise fall into disrepair | Consider individual requests for funding as and when they arise |  | Chair, Clerk | 2000
Support and develop our charitable trusts | Improve the Welcome Hall | The facility is in need to updating and could become a far more popular and effective asset for the village | Consult with management committee |  | Colin, Lynn
| Improve and support the Town Field Allotment Gardens | Allotment | Consult with management committee |  | Lynn
Support the social needs of all age groups within the Parish | Support the Trimley Station Trust | Trimley Station is a unique historical resource which can be saved for the village. | Liaise with the Trimley Station Trust. | Offer support in 2019 for stage 1 of the development. | Bryan | 5000
| Support Rosebury Cottage | The Café provides meals for the under privileged and vulnerable | Seek to provide funding to allow for further activities at the Cafe |  | David
| Encourage third party support organisations to set up within the village | While facilities such as Citizens Advice and Age Concern can be found in Felixstowe, there is no local facility within the village. | Make accommodation available for drop-in centres |  | Colin
Develop and improve the knowledge of Councillors | Provide funding for Councillor Training | We wish our councillors to be as highly trained as possible so they can make full use of local knowledge. | Offer high quality training to councillors through Suffolk Association of Local Councils and other sources, circulate training information. | Ongoing | All councillors and clerk. | £500 p.a.
| Develop a welcome pack and induction for new councillors. | Some new councillors find it difficult to understand procedures, protocols and practices. | Identify key issues and prepare documentation as needed. |  | Lynn and Clerk | Expenses
Improve communication with residents and other stake holders | Make best use of the website and Face Book page | Many residents use the internet and Social Media to keep up to date with local developments | Increase in volume, and more timely publication of information | By October 2020 | Colin / Andrew
| Use the Parish Magazine as a means on informing and engaging with residents. | Not all residents are active on line, we need an additional means of communicating developments | Aim to produce and distribute the magazine to all residents 3 times a year. | 2020-03-01 | Lynn with others | Expenses
| Seek feedback from residents | Ensure the activities of the Parish Council reflect the needs of residents | Develop consultation events to engage residents though, for example, parish meetings, drop in sessions or the APM | Annually | Chair, Clerk. | £1000 per annum
| Support local events | Parish funds should be spent on Parish activities | Identify ways in which we can support activities within the parish, such as Christmas celebrations, Carnival, Football tournament etc | Ongoing | Chair Clerk | Expenses
| Encourage Village cohesion | Trimley St Mary is a ribbon village with clusters of housing that do not always work together | Identify activities that bring the entire village together, make use of the Community Partnership Funding. |  | Lynn
Ensure the Parish Plan remains relevant | Monitor the changing demographics of the Parish | Changing populations have different needs | Obtain detailed demographic information and identify areas of future need | Annually | All councillors and clerk.